## Todo
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Change player skin |  | Forest | Fish | Harry | 7 Jan |  | Pending
Cut Attack Animation | Remove player attack animation have some unnecessary frame |  | Fish | Fish | 7 Jan | 11 Jan | Complete
Enemy attack |  | Forest | Fish | Fish | 7 Jan | 7 Jan | Complete
Enemy spawn |  | Forest | Fish | Fish | 7 Jan | 7 Jan | Complete
Player UI |  |  | Fish | Kuen | 7 Jan | 15 jan | In progress
Exp | EXP bar to show player exp |  | Fish | Kuen | 7 Jan | 7 Jan | Complete
HP | HP bar to show player hp |  | Fish | Kuen | 7 Jan | 15 jan | Complete
level system |  |  | Fish | Kuen | 7 Jan | 7 Jan | Complete
Equipment |  |  | Fish |  | 7 Jan
New village | Build a new village in a new scene | City | Fish | Kit | 7 Jan | 7 Jan | Complete
Mission |  | City | Fish | Kit | 7 Jan |  | In progress
Optimize player jump |  |  | Fish |  | 7 Jan
Map |  |  | Fish |  | 7 Jan
Transaction |  |  | Fish | Harry | 7 Jan |  | In progress
Player Attribute - UI |  |  | Fish | Fish | 7 Jan |  | In progress
Player Attribute |  |  | Fish | Fish | 7 Jan |  | In progress
Story |  |  | Fish |  | 7 Jan
Skill |  |  | Fish |  | 7 Jan
Item |  |  | Fish |  | 7 Jan
Classes |  |  | Fish |  | 7 Jan
Item drop |  |  | Fish |  | 7 Jan
Bag |  |  | Fish |  | 7 Jan
System menu |  |  | Fish |  | 7 Jan
All UI item should be private |  |  | Fish |  | 7 Jan
Up level animation |  |  | Fish |  | 7 Jan
Buff - UI |  |  | Fish |  | 7 Jan
min damage 1 | add a super algo to cal the 1 damage |  | Fish | kuen | 14 Jan | 15 jan | Complete
db and save |  |  | Fish | Fish | 14 Jan |  | In progress
cd |  |  | Fish | fish | 14 Jan
gcd |  |  | Fish | fish | 14 Jan
Refactor code | Refactor the code not done by ourselves |  | Fish |  | 18 Jan
Character Creation Scene | Only include job selection and name |  | Fish | Harry | 18 Jan |  | In progress

## Defect
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Camera will auto move | Seems related to attack function/animation of player | NA | Fish | Fish | 7 Jan | 7 Jan | Solved
Attack leg animation | When player attacking and move at the same time, leg will not move | NA | Fish |  | 7 Jan
Unusual Attack | Enemy will damage by player without player attack | Forest | Fish |  | 7 Jan
Player pass through terrain |  | Forest | Fish |  | 7 Jan
Enemy attack | Enemy could still attack once after its dead. It leads to the level up times cut to once only | Forest | Fish |  | 7 Jan