## Todo
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Change player skin |  | Forest | Fish | Harry | 7 Jan | 6 Feb | Cancel
Cut Attack Animation | Remove player attack animation have some unnecessary frame |  | Fish | Fish | 7 Jan | 11 Jan | Complete
Enemy attack |  | Forest | Fish | Fish | 7 Jan | 7 Jan | Complete
Enemy spawn |  | Forest | Fish | Fish | 7 Jan | 7 Jan | Complete
Player UI |  |  | Fish | Kuen | 7 Jan | 15 jan | In progress
Exp | EXP bar to show player exp |  | Fish | Kuen | 7 Jan | 7 Jan | Complete
HP | HP bar to show player hp |  | Fish | Kuen | 7 Jan | 15 jan | Complete
level system |  |  | Fish | Kuen | 7 Jan | 7 Jan | Complete
Equipment |  |  | Fish |  | 7 Jan
New village | Build a new village in a new scene | City | Fish | Kit | 7 Jan | 7 Jan | Complete
Mission |  | City | Fish | Kit | 7 Jan |  | In progress
Optimize player jump |  |  | Fish |  | 7 Jan
Map |  |  | Fish |  | 7 Jan
Transaction |  |  | Fish | Harry | 7 Jan |  | In progress
Player Attribute - UI |  |  | Fish | Fish | 7 Jan |  | In progress
Player Attribute |  |  | Fish | Fish | 7 Jan |  | In progress
Story |  |  | Fish |  | 7 Jan
Skill |  |  | Fish |  | 7 Jan
Item |  |  | Fish |  | 7 Jan
Classes |  |  | Fish |  | 7 Jan
Item drop |  |  | Fish |  | 7 Jan
Bag |  |  | Fish |  | 7 Jan
System menu |  |  | Fish |  | 7 Jan
All UI item should be private |  |  | Fish |  | 7 Jan
Up level animation |  |  | Fish |  | 7 Jan
Buff - UI |  |  | Fish |  | 7 Jan
min damage 1 | add a super algo to cal the 1 damage |  | Fish | kuen | 14 Jan | 15 jan | Complete
db and save |  |  | Fish | Fish | 14 Jan |  | In progress
cd |  |  | Fish | fish | 14 Jan
gcd |  |  | Fish | fish | 14 Jan
Tutorial |  |  | Fish |  | 30 Jan
Character Creation Scene | Only include job selection and name |  | Fish | Harry | 18 Jan |  | In progress
Adjust camera |  |  | Fish |  | 18 Jan
Light integration |  | Forest | Fish |  | 18 Jan
Log console |  |  | Fish |  | 18 Jan
Change scene |  |  | Fish | Fish | 23 Jan |  | Complete
Enemy status |  |  | Fish |  | 24 Jan
Void space | Void around the ground |  | Fish |  | 24 Jan
Refactor code | Refactor the code not done by ourselves |  | Fish |  | 18 Jan
set spawn object parent |  |  | Fish |  | 30 Jan
Check getComponenet success |  |  | Fish |  | 30 Jan
Make some public var NonSerialized |  |  | Fish |  | 30 Jan
Singletons | http://wiki.unity3d.com/index.php/Singleton |  | Fish |  | 30 Jan
Add HandleInput() | Change isAttacking, isLoading to Handle Input (state machines), can include game over state |  | Fish |  | 30 Jan
Add constraints to prefab | RequiredComponent, DisallowMultipleComponent, SelectionBase |  | Fish |  | 30 Jan
Link prefabs to prefabs | do not link instances to instances. |  | Fish |  | 30 Jan
Use scriptable objects for level data | http://kzunity.blogspot.hk/2015/05/scriptableobject_4.html |  | Fish |  | 30 Jan
Three Character share control method | http://gameprogrammingpatterns.com/command.html |  | Fish |  | 30 Jan
All spawn object should use resource pool |  |  | Fish |  | 30 Jan
Multiple same object should use flyweight | http://gameprogrammingpatterns.com/flyweight.html |  | Fish |  | 30 Jan

## Defect
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Camera will auto move | Seems related to attack function/animation of player | NA | Fish | Fish | 7 Jan | 7 Jan | Solved
Attack leg animation | When player attacking and move at the same time, leg will not move | NA | Fish |  | 7 Jan | 21 | Solved
Unusual Attack | Enemy will damage by player without player attack | Forest | Fish |  | 7 Jan
Player pass through terrain |  | Forest | Fish |  | 7 Jan
Enemy attack | Enemy could still attack once after its dead. It leads to the level up times cut to once only | Forest | Fish |  | 7 Jan
Save Object | Can't save object if the bag has not been enabled. | UI | Fish |  | 10 Mar
new char texture | the char in new char are so shinnydue to the texture in new char is modified by ghost | NewCharacter | Fish | Fish | 30 Mar

## Remark
Item | 0 - 99
Weapon | 100 - 199
Armor | 200 - 299