## Todo
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Change player skin |  | Forest | Fish | Harry | 2017-12-27 |  | In progress
Cut Attack Animation | Remove player attack animation have some unnecessary frame |  | Fish |  | 2017-12-27
Enemy attack |  | Forest | Fish | Fish | 2017-12-27 |  | In progress
Enemy spawn |  | Forest | Fish |  | 2017-12-31
UI - skill and menu |  |  | Fish | Kuen | 2017-12-31 |  | In progress
Exp | EXP bar to show player exp |  | Fish |  | 2017-12-31
HP | HP bar to show player hp |  | Fish |  | 2017-12-31
level system |  |  | Fish | Kuen | 2017-12-31 | 2018-01-06 | Complete
Equipment |  |  | Fish |  | 2017-12-31
New village | Build a new village in a new scene | City | Fish | Kit | 2017-12-31 |  | In progress
Mission |  | City | Fish |  | 2017-12-31
Optimize player jump |  |  | Fish |  | 2018-01-03
Map |  |  | Fish

## Defect
Issue | Description | Scene | Creator | PIC | Create date | Finish date | Status
Camera will auto move | Seems related to attack function/animation of player | NA | Fish | Fish | 2017-12-27 | 2018-01-03 | Solved
Attack leg animation | When player attacking and move at the same time, leg will not move | NA | Fish |  | 2017-12-31
Unusual Attack | Enemy will damage by player without player attack | Forest | Fish |  | 2018-01-04
Player pass through terrain |  | Forest | Fish